## Project Charter
Agile Project Charter
General Project Information
Project Name | Data Exchange between ABC Company and 3S Co., Ltd.
SCRUM Manager | Serena Choi
SCRUM team members | 4
Stakeholders | ABC Company(Interior design and decoration platform) 3S Co.,Ltd (3rd material supply company)
Expected Start Date | 2022-02-07
Expected Completion Date | 2022-03-08
Project Details
Mission | To achieve data exchange between ABC company and 3S Co.,Ltd about orders
Scope | This project is to develop a simple mini system to be used in the daily operations between ABC Company(Interior design and decoration platform) and 3S Co.,Ltd (3rd material supply company). The objective in the project is achieve the data interact of order when the order create. The project will be complete on 24/3/2022 and the scrum manager, Serena Choi will track the task process. The team member also will create the deliverables.
Success Metrics | The method of data interact acheived in automatically is the success metrics.
Date: | 2022-02-08

## Project Plan
Agile Project Plan
Project Name | Data Exchange between ABC Company and 3S Co., Ltd.
Project Manager | Serena Choi
Project Deliverable | To exchange data between ABC Company and 3S Co., Ltd.
Scope Statement | This project is to develop a simple mini system to be used in the daily operations between ABC Company(Interior design and decoration platform) and 3S Co.,Ltd (3rd material supply company).
Start Date | 2022-02-07
End Date | 2022-03-08
Overall Progress | 100%
Task Name | Responsible | Start | End | Days | Status
Sprint 1 | Kelly | 2022-02-07 | 2022-02-11 | 4 | Complete
Feature 1 - Account Management | Choco | 2022-02-07 | 2022-02-08 | 2 | Complete
Feature 2 - Account Management & Security | Serena | 2022-02-09 | 2022-02-10 | 1 | Complete
Feature 3 - Account Management | Wendy | 2022-02-10 | 2022-02-11 | 1 | Complete
Sprint 2 | Serena | 2022-02-13 | 2022-03-02 | 17 | Complete
Feature 4 - Security | Kelly | 2022-02-14 | 2022-02-16 | 2 | Complete
Feature 5 - Resources | Choco | 2022-02-17 | 2022-02-24 | 7 | Complete
Feature 6 - Security | Wendy | 2022-02-24 | 2022-03-02 | 6 | Complete
Sprint 3 | Choco | 2022-03-02 | 2022-03-09 | 7 | Complete
Feature 7 - Resources | Serena | 2022-03-02 | 2022-03-07 | 5 | Complete
Feature 8 - Resources | Kelly | 2022-03-07 | 2022-03-09 | 2 | Complete

## User Story
Agile User Story Template
Feature | User Story ID | As a <type of user> | I want to <perform some task> | so that I can <achieve some goal>
1 | 1 | Customer | create a new account | have an account to access the system
1 | 2 | Provider | create a new account | have an account to access the system
2 | 3 | Customer | enter username and password | get authenticated and gain access to the system
2 | 4 | Provider | enter username and password | get authenticated and gain access to the system
2 | 5 | Administrator | enter username and password | get authenticated and gain access to the system
3 | 6 | Customer | change my accounts information | update my perosnal information
3 | 7 | Provider | change my accounts information | update my perosnal and company information
3 | 8 | Administrator | review my accounts information | check if the information is accurate
4 | 9 | Administrator | verify provider accounts | ensure the accuracy of the provided information
4 | 10 | Administrator | delete certain accounts | prevent unauthorized users to get into the system
5 | 11 | Customer | upload cases | find and select a provider to design or decorate my place
5 | 12 | Customer | cancel cases | cancel the unwanted cases
5 | 13 | Administrator | verify cases | ensure the accuracy of the provided information
5 | 14 | Provider | look for cases | look for cases to work on
6 | 15 | Provider | apply cases | send applications to certain cases that I want to work on
6 | 16 | Provider | cancel case applications | cancel the unwanted case applications
6 | 17 | Administrator | verify case applications | ensure the accuracy of the provided information
6 | 18 | Customer | accept case applications | select a provider for a case if I'm satisfied with the case application
7 | 19 | Administrator | change the status of in-process cases | update them according to the case process
7 | 20 | Administrator | change the price of in-process cases | update them after discussions with customer and provider
8 | 21 | Provider | order materials for in-process cases | order certain materials that my cases required
8 | 22 | Provider | review previous material orders | double check the order details and check on the shipping status

## Product Backlog
Agile Product Backlog
Task Name | Story | Sprint Ready | Priority | Status | Story Points | Assigned to Sprint
Feature 1 | Yes | Yes | Medium | Complete | 16 | Yes
Feature 2 | Yes | Yes | High | Complete | 12 | Yes
Feature 3 | Yes | Yes | Low | Complete | 10 | Yes
Feature 4 | Yes | Yes | Medium | Complete | 27 | Yes
Feature 5 | Yes | Yes | High | Complete | 42 | Yes
Feature 6 | Yes | Yes | High | Complete | 36 | Yes
Feature 7 | Yes | Yes | High | Complete | 25 | Yes
Feature 8 | Yes | Yes | High | Complete | 23 | Yes

## Sprint Backlog
Sprint Backlog Template ( Remaining outstanding efforts in hours )
Sprint Number | 1 |  |  | Date | 2022-02-06 | 2022-02-07 | 2022-02-08 | 2022-02-09 | 2022-02-10 | 2022-02-11 | 2022-02-12 | 2022-02-13 | 2022-02-14 | 2022-02-15 | 2022-02-16 | 2022-02-17 | 2022-02-18 | 2022-02-19 | 2022-02-20 | 2022-02-21 | 2022-02-22 | 2022-02-23 | 2022-02-24 | 2022-02-25 | 2022-02-26 | 2022-02-27 | 2022-02-28 | 2022-03-01 | 2022-03-02 | 2022-03-03 | 2022-03-04 | 2022-03-05 | 2022-03-06 | 2022-03-07 | 2022-03-08 | 2022-03-09
|  |  |  | Weekday | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed
Backlog Item | Story Points | Responsible | Status | Original Estimate | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15 | Day 16 | Day 17 | Day 18 | Day 19 | Day 20 | Day 21 | Day 22 | Day 23 | Day 24 | Day 25 | Day 26 | Day 27 | Day 28 | Day 29 | Day 30 | Day 31 | Sprint Review
User Story #1 | 8 |  | Complete
Design the UI | 2 | Choco | Complete | 1 | [32 empty] | 0 | bar: Day 1
Create customer accounts table in database | 2 | Choco | Complete | 1 | [32 empty] | 0 | bar: Day 1
Coding | 3 | Choco | Complete | 3 | Day 1: 4 | 0
Testing & Debugging | 1 | Choco | Complete | 2 | Day 1: 2; Day 2: 1 | 0
User Story #2 | 8 |  | Complete
Design the UI | 2 | Choco | Complete | 1 | [32 empty] | 0 | bar: Day 2
Create provider accounts table in database | 2 | Choco | Complete | 1 | [32 empty] | 0 | bar: Day 2
Coding | 3 | Choco | Complete | 1 | Day 2: 2 | 0
Testing & Debugging | 1 | Choco | Complete | 1 | Day 2: 2 | 0
User Story #3 | 5 |  | Complete
Design the UI | 2 | Serena | Complete | 1 | [32 empty] | 0 | bar: Day 3
Coding | 2 | Serena | Complete | 1 | Day 3: 2 | 0
Testing & Debugging | 1 | Serena | Complete | 1 | [32 empty] | 0 | bar: Day 3
User Story #4 | 4 |  | Complete
Coding | 3 | Serena | Complete | 1 | [32 empty] | 0 | bar: Day 3
Testing & Debugging | 1 | Serena | Complete | 1 | Day 3: 2 | 0
User Story #5 | 3 |  | Complete
Create administrator accounts table in database | 1 | Serena | Complete | 1 | [32 empty] | 0 | bar: Day 3
Coding | 1 | Serena | Complete | 1 | Day 4: 2 | 0
Testing & Debugging | 1 | Serena | Complete | 1 | [32 empty] | 0 | bar: Day 4
User Story #6 | 4 |  | Complete
Design the UI | 1 | Wendy | Complete | 1 | [32 empty] | 0 | bar: Day 4
Coding | 2 | Wendy | Complete | 3 | Day 4: 3 | 0
Testing & Debugging | 1 | Wendy | Complete | 1 | Day 4: 1; Day 5: 2 | 0
User Story #7 | 3 |  | Complete
Design the UI | 1 | Wendy | Complete | 1 | [32 empty] | 0 | bar: Day 5
Coding | 1 | Wendy | Complete | 1 | [32 empty] | 0 | bar: Day 5
Testing & Debugging | 1 | Wendy | Complete | 1 | [32 empty] | 0 | bar: Day 5
User Story #8 | 3 |  | Complete
Design the UI | 1 | Wendy | Complete | 1 | [32 empty] | 0 | bar: Day 5
Coding | 2 | Wendy | Complete | 1 | [32 empty] | 1 | bar: Day 5
User Story #9 | 3 |  | Complete
Design the UI | 3 | Kelly | Complete | 1 | [32 empty] | 0 | bar: Day 5
Coding | 7 | Kelly | Complete | 7 | Day 8: 8 | 0
Testing & Debugging | 2 | Kelly | Complete | 1 | Day 9: 2 | 0
User Story #10 | 3 |  | Complete
Design the UI | 3 | Kelly | Complete | 1 | [32 empty] | 0 | bar: Day 9
Coding | 10 | Kelly | Complete | 9 | Day 9: 5; Day 10: 5 | 0
Testing & Debugging | 2 | Kelly | Complete | 1 | Day 10: 3 | 0
User Story #11 | 14 |  | Complete
Design the UI | 1 | Choco | Complete | 1 | [32 empty] | 0 | bar: Day 11
Create cases table in database | 2 | Choco | Complete | 1 | [32 empty] | 0 | bar: Day 11
Coding | 10 | Choco | Complete | 8 | Day 11: 6; Day 12: 2 | 0
Testing & Debugging | 1 | Choco | Complete | 1 | [32 empty] | 1 | bar: Day 12
User Story #12 | 8 |  | Complete
Design the UI | 1 | Choco | Complete | 1 | [32 empty] | 0 | bar: Day 12
Coding | 6 | Choco | Complete | 4 | Day 12: 4 | 0
Testing & Debugging | 1 | Choco | Complete | 1 | Day 15: 2 | 0
User Story #13 | 8 |  | Complete
Design the UI | 1 | Choco | Complete | 1 | [32 empty] | 0 | bar: Day 15
Coding | 6 | Choco | Complete | 5 | Day 15: 5; Day 16: 2 | 0
Testing & Debugging | 1 | Choco | Complete | 1 | [32 empty] | 0 | bar: Day 16
User Story #14 | 12 |  | Complete
Design the UI | 1 | Choco | Complete | 1 | [32 empty] | 0 | bar: Day 16
Coding | 10 | Choco | Complete | 10 | Day 16: 4; Day 17: 8 | 0
Testing & Debugging | 1 | Choco | Complete | 1 | Day 18: 3 | 0
User Story #15 | 12 |  | Complete
Design the UI | 2 | Wendy | Complete | 1 | [32 empty] | 0 | bar: Day 18
Create cases applications table in database | 2 | Wendy | Complete | 1 | [32 empty] | 0 | bar: Day 18
Coding | 7 | Wendy | Complete | 6 | Day 18: 3; Day 19: 4 | 0
Testing & Debugging | 1 | Wendy | Complete | 1 | [32 empty] | 1 | bar: Day 19
User Story #16 | 8 |  | Complete
Design the UI | 1 | Wendy | Complete | 1 | [32 empty] | 0 | bar: Day 19
Coding | 6 | Wendy | Complete | 4 | Day 19: 2; Day 22: 3 | 0
Testing & Debugging | 1 | Wendy | Complete | 1 | [32 empty] | 0 | bar: Day 22
User Story #17 | 8 |  | Complete
Design the UI | 1 | Wendy | Complete | 1 | [32 empty] | 0 | bar: Day 22
Coding | 6 | Wendy | Complete | 4 | Day 22: 3; Day 23: 1 | 0
Testing & Debugging | 1 | Wendy | Complete | 1 | [32 empty] | 0 | bar: Day 23
User Story #18 | 8 |  | Complete
Design the UI | 1 | Wendy | Complete | 1 | [32 empty] | 0 | bar: Day 23
Coding | 6 | Wendy | Complete | 4 | Day 23: 5 | 0
Testing & Debugging | 1 | Wendy | Complete | 1 | Day 24: 2 | 0
User Story #19 | 12 |  | Complete
Design the UI | 1 | Serena | Complete | 1 | [32 empty] | 0 | bar: Day 24
Coding | 10 | Serena | Complete | 9 | Day 24: 5; Day 25: 5 | 0
Testing & Debugging | 1 | Serena | Complete | 1 | [32 empty] | 1 | bar: Day 25
User Story #20 | 13 |  | Complete
Design the UI | 1 | Serena | Complete | 1 | [32 empty] | 0 | bar: Day 25
Coding | 11 | Serena | Complete | 10 | Day 25: 1; Day 26: 8 | 0
Testing & Debugging | 1 | Serena | Complete | 1 | Day 29: 2 | 0
User Story #21 | 15 |  | Complete
Design the UI | 1 | Kelly | Complete | 1 | [32 empty] | 0 | bar: Day 29
Create material details and order tables in database | 2 | Kelly | Complete | 1 | [32 empty] | 0 | bar: Day 29
Coding | 11 | Kelly | Complete | 11 | Day 29: 4; Day 30: 8 | 0
Testing & Debugging | 1 | Kelly | Complete | 1 | Day 31: 3 | 0
User Story #22 | 8 |  | Complete
Design the UI | 1 | Kelly | Complete | 1 | [32 empty] | 0 | bar: Day 31
Coding | 7 | Kelly | Complete | 3 | Day 31: 3 | 1
Total | 170 |  | Complete | 153 | 0 | 8 | 7 | 8 | 8 | 8 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 8 | 8 | 7 | 5
|  |  |  | Estimated Hours | 153 | 145 | 137 | 129 | 121 | 113 | 113 | 113 | 105 | 97 | 89 | 81 | 73 | 73 | 73 | 65 | 57 | 49 | 41 | 33 | 33 | 33 | 25 | 17 | 9 | 1 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Actual Hours | 182 | 174 | 167 | 159 | 151 | 143 | 143 | 143 | 135 | 127 | 119 | 111 | 103 | 103 | 103 | 95 | 87 | 79 | 71 | 63 | 63 | 63 | 55 | 47 | 39 | 31 | 23 | 23 | 23 | 15 | 7 | 0
-

## Test Plan
Agile Test Plan
Project Name | Data Exchange between ABC Company and 3S Co., Ltd. |  | Browser: | Google Chrome
Test Case ID | 1 |  | Version: | 1.0
Written By: | Choco |  | Description: | To test if every feature meets the expected result
Tested By: | Serena |  | Tested On: | 2022-03-07
Test # | Date | Action | Expected Results | Actual Results | Pass?
1 | 2022-02-09 | create a new customer account | create customer account and update to database, display messages accurately | customer account created and database updated successfully, messages displayed accurately | Pass
2 | 2022-02-09 | create a new provider account | create provider account and update to database, display messages accurately | provider account created and database updated successfully, messages displayed accurately | Pass
3 | 2022-02-10 | login customer account | login failed or succeed, display messages accurately | login successfully, messages displayed accurately | Pass
4 | 2022-02-10 | login provider account | login failed or succeed, display messages accurately | login successfully, messages displayed accurately | Pass
5 | 2022-02-10 | login administrator account | login failed or succeed, display messages accurately | login successfully, messages displayed accurately | Pass
6 | 2022-02-11 | customer changes account information | update database, display messages accurately | data updated into database, messages displayed accurately | Pass
7 | 2022-02-11 | provider changes account information | update database, display messages accurately | data updated into database, messages displayed accurately | Pass
8 | 2022-02-12 | administrator reviews account information | display related data | data displayed successfully | Pass
9 | 2022-02-17 | administrator verifies provider accounts | change certain provider account status, database updated, provider login succeed or failed due to changes | several provider account status changed, database updated successfully, provider login succeed or failed due to changes | Pass
10 | 2022-02-17 | administrator deletes certain accounts | certain customer or provider accounts deleted, related data status updated in database, related accounts can no longer login | several customer and provider accounts deleted, related data status updated in database, related accounts login failed | Pass
11 | 2022-02-18 | customer uploads cases | update database, display messages accurately | database updated, messages displayed accurately | Pass
12 | 2022-02-21 | customer cancels cases | certain cases cancelled, related changes could be viewed in "My Account" / "Look for Cases" | certain cases cancelled, related changes being viewed in "My Account" / "Look for Cases" | Pass
13 | 2022-02-22 | administrator verifies cases | change certain cases status, database updated, related customer could view the changes, "Verified" cases displays in "Look for Cases" | several cases status changed, database updated, related customer could view the changes, "Verified" cases displayed in "Look for Cases" | Pass
14 | 2022-02-24 | different accounts look for cases | all accounts could look for cases, but only providers could apply cases when clicked in case "Details", others will display error messages | all accounts could look for cases, but only providers could apply cases when clicked in case "Details", others displayed error messages | Pass
15 | 2022-02-25 | provider applies cases | cases applied, display messages accurately, database updated, administrator could view the application | cases applied, messages displayed accurately, database updated, administrator could view the application | Pass
16 | 2022-02-28 | provider cancels case applications | certain case application cancelled, related customer could view the changes | several case application cancelled, related customer could view the changes | Pass
17 | 2022-03-01 | administrator verifies case applications | change certain case applications status, database updated, related provider could view the changes | several case applications status changed, database updated, related provider could view the changes | Pass
18 | 2022-03-02 | customer accepts case applications | case application accepted, database changed, related providers that applied the case could view the case & application status changed | case application accepted, database changed, related providers that applied the case could view the case & application status changed | Pass
19 | 2022-03-03 | administrator changes the status of in-process cases | status changed, database updated, related customer & provider could view the changes | status changed, database updated, related customer & provider could view the changes | Pass
20 | 2022-03-07 | administrator changes the price of in-process cases | price changed, database updated, related customer & provider could view the changes | price changed, database updated, related customer & provider could view the changes | Pass
21 | 2022-03-09 | provider orders materials for in-process cases | order details updated to database, display messages accurately | order details updated to database, display messages accurately | Pass
22 | 2022-03-09 | provider reviews previous material orders | display previous order details | displayed previous order details successfully | Pass